Plan of Operation Sample Table for One Activity – Provide a short narrative and a Table for each activity with the Objectives and Outcomes (use this format for the table)

|  |
| --- |
| **Direct Academic Services to ABC High School Students**  |
| **Objective:** To provide opportunities for 11th gr. students at ABC High School to attend remedial mathematics and English/language arts support to increase baseline assessment scores.**Projected** **Outcome:** By the end of October 2019, 260 11th gr. students will have had three opportunities to participate in remedial mathematics and English/language arts classes at their GEAR UP school site. Of the 260 11th gr. students, 60% will increase their pretest baseline scores by 5 to 10 points by the end of the classes.  |
| **Activity Description** | **Implementation Process** | **Activity Date** | **Expected Participants, Per Session** | **Evaluation Plan** | **Date (s)** | **Person (s) Responsible** |
| Remedial Classes  | 1. Hold information session for parents and students
2. Identify students who need remediation
3. Work with students to complete remediation courses.
4. Follow-up with students to compare PARCC assessment and school unit assessment scores
 | Fall 2018Spring 2019Summer 2019 |  40(260 total) | 1. Monitor student progress on course exams, assignments, and compare to pre-test baseline score. 2. Student self-report on remedial class experience3. Track students who complete remedial class during sessions and on PARCC assessments | Planning10/2018 thru 12/2018, OngoingRecruitment Registration12/2018 thru 2/2019Classes\*6/2019 to 8/2019 and \*9/2019 thru 10/2019 | 1. August Brown, project director2. Aaron Jupiter,GEAR UP SCHOOL coordinator3. June Stars, project evaluator  |