Plan of Operation Sample Table for One Activity – Provide a short narrative and a Table for each activity with the Objectives and Outcomes (use this format for the table)

| Direct Academic Services to ABC High School Students |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: To provide opportunities for 11th gr. students at ABC High School to attend remedial mathematics and English/language arts support to increase baseline assessment scores. Projected Outcome: By the end of October 2019, 260 11th gr. students will have had three opportunities to participate in remedial mathematics and English/language arts classes at their GEAR UP school site. Of the 260 11th gr. students, 60% will increase their pretest baseline scores by 5 to 10 points by the end of the classes. |  |  |  |  |  |  |
| Activity Description | Implementation Process | Activity Date | Expected Participants, Per Session | Evaluation Plan | Date (s) | Person (s) Responsible |
| Remedial Classes | - Hold information session for parents and students - Identify students who need remediation - Work with students to complete remediation courses. - Follow-up with students to compare PARCC assessment and school unit assessment scores | Fall 2018 Spring 2019 Summer 2019 | 40 (260 total) | 1. Monitor student progress on course exams, assignments, and compare to pre-test baseline score. 2. Student self-report on remedial class experience 3. Track students who complete remedial class during sessions and on PARCC assessments | Planning 10/2018 thru 12/2018, Ongoing Recruitment Registration 12/2018 thru 2/2019 Classes *6/2019 to 8/2019 and *9/2019 thru 10/2019 | 1. August Brown, project director 2. Aaron Jupiter, GEAR UP SCHOOL coordinator 3. June Stars, project evaluator |